## Sheet1
IT PROJECT RISK ANALYSIS TOOL
A - Project Management and Governance |  | Score (Max 3)
Has consideration been put in the current project scope and been well defined? |  | 0
Have sufficient processes been put in place to minimize the lack of accountability when things go wrong? |  | 0
Does the project have a selection of stakeholders which accurately represent the project? |  | 0
Are there any gaps of key roles at any level of the project? |  | 0
Have schedules been completed? |  | 0
Are the milestones and deadlines in place realistic and achievable? |  | 0
Has there been minimal turnover in leadership and staff positions? |  | 0
0/28
B - Project Development and Training
Are there actions in place to ensure no development is continued during a code freeze? |  | 0
Are there processes in place to ensure decisions are not based off optimism? |  | 0
Is there processes/plans to give end users adequate training prior to the go-live? |  | 0
0/9
C - Implementation / Go-Live
Have you ensured all requirements have been completed prior to the rollout? |  | 0
Has the implementation strategy been reviewed and chosen to be most appropriate? |  | 0
Has there been consideration into support for end users after Rollout? |  | 0
Are the phases of implementation identified in planning being followed in rollout? |  | 0
Has a plan been developed to ensure no risks are carried into the Go-Live? |  | 0
0/16
D - Planning & Requirements
Has appropriate research been done for selection of vendor? |  | 0
Has enough planning been done for this size of project? Including goals, phases, and deadlines? |  | 0
Have all user requirements been laid out and assessed? |  | 0
Are the current negotiations between client and vendor clear and suitable for long term agreement? |  | 0
0/13
E - Project Finance
Have measures been put in place to ensure the budget remains on track? |  | 0
Has the budget been properly reviewed by personnel with experience in similar projects? |  | 0
Is there processes in place to mitigate potential delays and the associated costs? |  | 0
0/10
F - Communication & Collaboration
Do team members know what their role and responsibilities consist of at all project levels? |  | 0
Is there processes in place to ensure there has been a continued presence by the top-level in the project? |  | 0
Is there transparency between client, vendor, team members, and end users? |  | 0
Are end users being involved during the project phases as a form of feedback and training? |  | 0
0/13
G – Risk and Quality Assurance
Has the system been tested and troubleshooted to the full extent before implementation? |  | 0
Is there currently measures in place to deal with failed test cases? |  | 0
Have all risks been mitigated by carrying out a full readiness assessment? |  | 0
0/11
| ANALYSIS TOTAL | 0/100